## Strip Info
| Season | Buyer | Dept | Style no/PID | Wash Name/Color | PO No | Ex Factory Date | Quantity
Target Aystralia | Winter/Summer | Target Aystralia | Ladies/Mens | 4150189204 | DARK BLUE | 2148209 | 2021-12-30 | 1001
| W22/S22 | T-Aus | LD/MN | 4150189204 | DARK BLUE | 2148209 | 123021 | 1001 | W22/S22::T-Aus::LD/MN::4150189204::DARK BLUE::2148209::123021::1001
Target USA | C1/C2/C3/C4 | Target USA | Big Boyes /ITB /Mens | 9WEY8 | HILTOP | 8905067 | 2021-12-28 | 16875
| C122 | T-USA | BB/ITB/MN | 9WEY8 | HILTOP | 8905067 | 122821 | 16875 | C122::T-USA::BB/ITB/MN::9WEY8::HILTOP::8905067::122821::16875
Kontoor | Summer Spring/ Fall Winter | Kontoor | TBA | 103408928 | RENEGADE | 450025755000100 | 2022-02-21 | 3000
| SS22/FW22 | KB | TBA | 103408928 | RENEGADE | 450025755000100 | 22122 | 3000 | SS22/FW22::KB::TBA::103408928::RENEGADE::450025755000100::22122::3000
GU | Summer Spring/ Fall Winter | GU | Kids/Mens | 60121H001A | #60 | P6021-329799-001 | 2022-10-12 | 5000
| SS22/FW22 | GU | KD/MN | 60121H001A | #60 | P6021-329799-001 | 101222 | 5000 | SS22/FW22::GU::KD/MN::60121H001A::#60::P6021-329799-001::101222::5000

## Planning Range
Order Sewing Start date depends on
Ivents | Data Type | Criteria | Data Type | Criteria | Result
Fabric In-house | Date | Last date among these 3 events | 2021-11-10 | 2021-11-15 | 2021-11-15
Sewing Accessories In-house | Date |  | 2021-11-15 |  |  | List of holidays
Sample Approval | Date |  | 2021-11-13 |  |  | 2021-12-16
Pre-production | no of working days | Add with previous event | 7 |  | 2021-11-23 | 2022-02-21
2022-03-26
2022-04-14
2022-05-01
2022-05-02
2022-05-03
Order Sewing Start date depends on | [5 empty] | 2022-05-04
Ivents | Data Type | Criteria | Data Type | Criteria | Result | 2022-05-05
Ex factory Date | Date | From Order Recap | 2021-12-20 |  | 2021-12-20 | 2022-05-06
Inspection to Ex factory | no of working days | Subtract from previous event | -2 |  | 2021-12-18 | 2022-05-07
Wash close to Inspection | no of working days | Subtract from previous event | -2 |  | 2021-12-14 | 2022-05-08
Sewing Close to Wash Close | no of working days | Subtract from previous event | -4 |  | 2021-12-09 | 2022-05-09
2022-08-15
Formulas:
Criteria = MAX([Data Type]:D5)
Result = [Criteria]
Result = WORKDAY.INTL(F3,[Data Type],16,[List of holidays, row above]:L17)

## Line Properties
Line |  |  |  | Style |  |  |  | Efficiency Back Calculation |  |  | Monthly Efficiency
|  |  | Fomula |  |  |  | Formula | Input | Productivity per hour | 152 | Sum (Style wise SMV * quantity)/Total available Minute
Input | SMV | 18.3 |  | Input | SMV | 18.3 |  | Input | SMV | 18.3
Input | No of Manpower | 80 |  | Input | No of Manpower | 80 |  | Input | No of Manpower | 80 | Line No | Style |  |  | Day | 1 | 2 | 3 | Produced Minutes | Available Minutes | Efficiency
Input | Working hours Per day | 10 |  | Input | Efficiency | 58% | [6 empty] | Man Poewr | SMV | Working Hr | 10 | 10 | 11
Input | Line efficiency | 66% | [8 empty] | 1 | Style-1 | 80 | 19.5 |  | 2000 | 2000 | 0 | 78000 | 96000 | 81.25%
|  |  |  | Output | Available Mins per Hour | 4800 | I3*60 | Input | Efficiency | 57.95% |  | Style-2 | 80 | 18 |  | 0 | 0 | 600 | 10800 | 52800 | 20.45%
Output | Available Minutes per Day | 48000 | C2*C3*60 | Output | Produced Mins per Hour | 2784 | I3*60*I4 |  |  |  | 2 | Style-3 | 78 | 21 |  | 1600 | 1600 | 1600 | 100800 | 145080 | 69.48%
Output | Produced Minutes per Day | 31680 | C2*C3*C4*60 | Output | Productivity per hour | 152 | ROUND(I7/I2,0) |  |  |  | Plan Total |  | 238 |  |  | 3600 | 3600 | 2200 | 189600 | 293880 | 64.52%
Output | Productivity per Day | 1731 | ROUND(C8/C2,0)

## Style Property
Product Type | Build up day | Day 1 0-10Hr | Day 2 11-20Hr | Day 3 21-30Hr | Day 4 31-40Hr | Day 5 41-50Hr | Day 6 51-60Hr | Day 7 61-70Hr | Day 8 71-80Hr | Why in Hr based build up instead of day based?
Very Basic | 2 | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100%
Basic | 3 | 35% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 200 | Day-1 | Day-2 | Day-3 | Day-4 | Day-5 | Day-6 | Day-7 | Day-8 | 55 Hr Production | Average/Hr
Medium | 4 | 25% | 40% | 60% | 80% | 100% | 100% | 100% | 100% | 8 | 400 | 640 | 960 | 1280 | 1600 | 1600 | 1400 |  | 7880 | 143.2727
Critical | 5 | 15% | 30% | 50% | 70% | 90% | 100% | 100% | 100% | 9 | 450 | 720 | 1080 | 1440 | 1800 | 1800 | 200 |  | 7490 | 136.1818
Very Critical | 7 | 0% | 20% | 30% | 45% | 65% | 80% | 90% | 100% | 10 | 500 | 800 | 1200 | 1600 | 2000 | 1000 |  |  | 7100 | 129.0909
[10 empty] | 11 | 550 | 880 | 1320 | 1760 | 2200 |  |  |  | 6710 | 122
Selected option for planning
No Changeover/SMED