## TNA-2-08-2022
0
Factory | Season | Style | Fabric | Mill Name | Wash Name | Image | Quantity | New/CF | Order Confirmation/ BA Date/ VA Date | Handover date | Initial Plan Date | CMS date | Final Plan Date | Wash Sample Approval Date | Proto/Fit Sample Approval Date | Internal Test Completion Date | CFT Meeting Date | Tollgate Meeting Date | PPT Completion Date | Fabric Booking | Fabric Delivery | Fabric In-house | Trims In-house Status | Pre-production Completion Date | Shadeband Submission Date | Shadeband Approval Date | PP/GSA Sample Approval Date | Size Set Sample Completion Date | Internal TPR Date | TPR Date | PCD Date | Sewing Start Date | Wash Start Date | DUPRO Date | Garment Test/TOP Test Pass Report Date | FRI/VSI/Final Inspection Date | REMARKS
CAL | C3-22 Fall | Z8TK29: GFMN SLIM STRAIGHT DENIM | STOLZ | AM | Zinger |  | 37212 | New | 2020-12-07 | 2021-04-06 | 2020-12-17 | 2021-02-05 | 2021-02-12 | 2020-12-22 | 2021-02-04 | 2020-12-12 | 2020-12-14 | 2020-12-28 | 2021-02-24 | 2020-12-08 | 2021-01-27 | 2021-02-26 | 2021-02-26 | 2021-03-05 | 2021-03-08 | 2021-03-10 | 2021-02-19 | 2021-02-26 | 2021-03-01 | 2021-03-03 | 2021-03-06 | 2021-03-07 | 2021-03-11 | 2021-03-17 | 2021-03-24 | 2021-04-05 |  | 125676
CGL | C3-22 Fall | 10YXYP: GFMN SKINNY DENIM | STOLZ | AM | Pyle |  | 15582 | New | 2020-12-07 | 2021-04-06 | 2020-12-17 | 2021-02-05 | 2021-02-12 | 2020-12-22 | 2021-02-04 | 2020-12-12 | 2020-12-14 | 2020-12-28 | 2021-02-24 | 2020-12-08 | 2021-01-27 | 2021-02-26 | 2021-02-26 | 2021-03-05 | 2021-03-08 | 2021-03-10 | 2021-02-19 | 2021-02-26 | 2021-03-01 | 2021-03-03 | 2021-03-06 | 2021-03-07 | 2021-03-11 | 2021-03-17 | 2021-03-24 | 2021-04-05 |  | 104046
Planning | Merchant | Merchant | Merchant | Merchant | Merchant | Merchant | Merchant | Merchant | Merchant | Merchant | Planning | Merchant | Planning | PD &D | Sample | PD &D | Merchant | Merchant | Merchant | Merchant | Merchant | Merchant | Merchant | Factory | Washing Plant | Merchant | Sample | Sample | Factory | Factory | Factory | Factory | Washing Plant | Factory | Merchant | Factory | Stakeholder
[9 empty] | 1 Day Prior from Fabric Booking date | Based on Required ISD | 10 Days from Order confirmation | 60 Days prior from Handover date | 7 Days from CMS date | 15 Days from Order confirmation | 15 Days prior from PP Approval date | 2 Days Prior CFT meeting | 7 Days after Order confirmation | 21 Days from order confirmation | 7 Days Prior from TPR date | 50 Days Prior from Fabric Delivery date | 30 Days Prior from Fabric In-house date | 7 Days Prior from Pre-production completion date | Sewing Trim: Same as fab inh Finshing Trim: 7 Days within PCD | 1 Day Prior from PCD Date | 3 days after Pre-production completion date | 2 Days after Submission | 7 Days prior from Size Set | 3 Days prior from Internal TPR | 2 Days prior from TPR | 3 Days prior from PCD | 30 Days prior from FRI date | 1 Day from PCD | 1 day from shadeband approval | 7 days from shadeband approval | 7 days from DUPRO | 1 Day Prior from Handover Date
CAL | C3-22 Fall | Z8TK29: GFMN SLIM STRAIGHT DENIM | STOLZ | AM | Zinger |  | 37212 | New | 2021-05-17 | 2021-09-14 | 2021-05-27 | 2021-07-16 | 2021-07-23 | 2021-06-01 | 2021-07-15 | 2021-05-22 | 2021-05-24 | 2021-06-07 | 2021-08-04 | 2021-05-18 | 2021-07-07 | 2021-08-06 | 2021-08-06 | 2021-08-13 | 2021-08-16 | 2021-08-18 | 2021-07-30 | 2021-08-06 | 2021-08-09 | 2021-08-11 | 2021-08-14 | 2021-08-15 | 2021-08-19 | 2021-08-25 | 2021-09-01 | 2021-09-13 |  | 125998
level | [8 empty] | 4.1 | 0 |  | 1.1 | 2.1 | [10 empty] | 3.1 | [6 empty] | 2.2 | 3.1 |  |  |  | 1.2
depandant | [9 empty] | 0 |  | 0 | 1.1 | [10 empty] | 2.2 | [6 empty] | 1.2 | 2.2 |  |  |  | 0
[7 empty] | 90006 |  | 2263-04-07 02:24 |  | 2263-05-03 | [26 empty] | 222687.1
Formulas:
Order Confirmation/ BA Date/ VA Date = [Fabric Booking]-1
Order Confirmation/ BA Date/ VA Date = SUM(J3:[Order Confirmation/ BA Date/ VA Date, row above])
Initial Plan Date = [Order Confirmation/ BA Date/ VA Date]+10
Initial Plan Date = SUM(L3:[Initial Plan Date, row above])
CMS date = [Handover date]-60
Final Plan Date = [CMS date]+7
Wash Sample Approval Date = [Order Confirmation/ BA Date/ VA Date]+15
Proto/Fit Sample Approval Date = [PP/GSA Sample Approval Date]-15
Internal Test Completion Date = [CFT Meeting Date]-2
CFT Meeting Date = [Order Confirmation/ BA Date/ VA Date]+7
Tollgate Meeting Date = [Order Confirmation/ BA Date/ VA Date]+21
PPT Completion Date = [TPR Date]-7
Fabric Booking = [Fabric Delivery]-50
Fabric Delivery = [Fabric In-house]-30
Fabric In-house = [Pre-production Completion Date]-7
Trims In-house Status = [Fabric In-house]
Pre-production Completion Date = [PCD Date]-1
Shadeband Submission Date = [Pre-production Completion Date]+3
Shadeband Approval Date = [Shadeband Submission Date]+2
PP/GSA Sample Approval Date = [Size Set Sample Completion Date]-7
Size Set Sample Completion Date = [Internal TPR Date]-3
Internal TPR Date = [TPR Date]-2
TPR Date = [PCD Date]-3
PCD Date = [FRI/VSI/Final Inspection Date]-30
Sewing Start Date = [PCD Date]+1
Wash Start Date = [Shadeband Approval Date]+1
DUPRO Date = [Shadeband Approval Date]+7
Garment Test/TOP Test Pass Report Date = [DUPRO Date]+7
FRI/VSI/Final Inspection Date = [Handover date]-1
Note on U3: Microsoft Office User: Considering 50 Days Production Lead Time
Note on V3: Microsoft Office User: Considering FCL & Faster Vessel and 30 Days from Ex-mill to Inhouse
Note on W3: Microsoft Office User: Ex-mill to In-house: India: 25 Days, China: 30 days, HK: 25 Days, Thailand: 30 Days Pakistan: 42 days
Note on X3: Microsoft Office User: Sewing Trim: Same as fab inh Finshing Trim: 7 Days within PCD
Note on U8: Microsoft Office User: Considering 50 Days Production Lead Time
Note on V8: Microsoft Office User: Considering FCL & Faster Vessel and 30 Days from Ex-mill to Inhouse
Note on W8: Microsoft Office User: Ex-mill to In-house: India: 25 Days, China: 30 days, HK: 25 Days, Thailand: 30 Days Pakistan: 42 days
Note on X8: Microsoft Office User: Sewing Trim: Same as fab inh Finshing Trim: 7 Days within PCD